


UPPER SOUTHAMPTON MUNICIPAL AUTHORITY
Meeting –July 27, 2026

The Meeting opened with the Pledge of Allegiance to the Flag.

Call to Order: The Regular Meeting of the Upper Southampton Municipal Authority was called to order on Monday, July 27, 2026, at 6:30 P.M. at the Authority Building, 945 Street Rd, Southampton, PA by Chair, Joseph (Joe) Gerace.

Members Present:	Joseph (Joe) Gerace, Chairman
James (Jim) Monaghan, Vice-Chair
Paul Angermeier, Secretary 
Timothy (Tim) U’Selis, Treasurer
			Evelyn (Evy) Brennan, Asst. Sec’y/Treasurer 

Administration:	Barbara A. O’Neill, Manager
			Savanna Bolger, Recording Secretary 
			Todd Savarese, Solicitor


1. Public Comment
None.

2.  Approve Agenda  
Motion by Mr. Angermeier to approve the agenda for the July 27, 2026, meeting. 

Second by Mr. Monaghan
Questions on the motion – none.
Poll of the Board
Motion carried unanimously.

3.  Presentation of Minutes – Meeting June 22, 2026.
Motion by Ms. Brennan to approve the minutes of the June 22, 2026, meeting.

Second by Mr. Angermeier.
Questions on the motion – none.
Poll of the Board. 		
Motion carried unanimously.

4. Treasurer’s Report (See Attached)
Motion by Mr. U’Selis to accept the Treasurer’s Report as presented.

Second by Ms. Brennan
Questions on the motion – none.
Poll of the Board.
Motion carried unanimously.


5. Bills Presented for Payment, Ratified Bill List and Credit Card Accounting
Motion by Mr. Monaghan to accept the bills for payment, ratified bill list, and credit card accounting as presented.

Second by Mr. U’Selis.
Questions on the motion: None	
Poll of the Board.
Motion carried unanimously.

7. Reports 
A) Rebecca Mason’s report stated the following:

MCPS 
· Lower Southampton letter confirming that the detour can utilize Township roads is forthcoming.
· ARV-1 install will commence upon receipt of PennDOT permit.
· IMPROVEMENTS PROJECT
· Compaction grouting is completed. Rebar was been delivered.
· Construction is currently about 2 weeks ahead of schedule. 

PA DEP
· DEP response to the 2025-Chapter 94 filing received July 15..
· DEP has requested additional information and corrections to the report.
· DEP has also instituted a connection ban, effective immediately.
· USMA has 90 days to respond with CAP.
SKYTOP
· Permit has been submitted to PA DEP.

MAPLE AVE WATER MAIN
· KBC is close to completing the installation of the main, service connections will start July 27th
· PennDOT approved the detour plan which will be implemented during the service connection phase. 

2025 MIRIA GRANT
· A mandatory pre bid meeting was held on July 27th 
· Project milestone dates:
· Advertise on PennBid: Complete
· Mandatory Pre-Bid Meeting: July 27
· Bids DUE: August 11
· Recommendation of award: August Authority Meeting
· Notice to proceed: September 1


RRA & ERP CERTIFICATION TO DEP
· RRA has been updated and certified
· ERP update and certification are due December 31, 2026. Entech will begin reviewing ERP from 2021 and make necessary updates. 

CONSUMER CONFIDENCE REPORT
· CCR certifications are due by October 1, 2026.

ANNUAL WATER ALLOCATION PERMIT 
· Annual report is in the information gathering phase; due September 8th.

GIS SERVICES
· Training session with USMA staff regarding integrating 1Mark into USMA’s existing GIS Program.

B) Solicitor, Todd Savarese gave the following report:

Mr. Savarese had no formal report for the Board.

C) Manager, Barbara O’Neill gave the following report:
PA Water Specialties would like permission to send follow up letters to non-compliant backflow preventer properties with a notification of possible service interruption.
· Mr. Savarese suggested the Board pass a Resolution formalizing the Authority’s service termination and/or discontinuance policy.  Resolution will be passed at a future meeting.

We have finalized the union contract, with a memorandum of understanding regarding the use of the overtime wheel to follow, to be considered under old business.

The NAVFAC inter-municipal agreement has not yet been finalized as the Navy has delayed Charter Court and Estate Lance property connections with the expectation of adding them to the next ESCA forthcoming in the next few months.

MIRIA reminders will go out to the 20+ residents who have not responded to the letters advising the availability of no cost connection to the system.  

8. New Business
· Consideration of Payment Application #1
· KBC Construction LLC- Maple Avenue Water Main

Motion by Mr. Angermeier to approve the payment as presented.

Second by Ms. Brennan.
Questions on the motion – none.
Poll of the Board.
Motion carried unanimously.
· Consideration of Payment Application #1
· Blooming Glen Construction- MCPS Improvements

Motion by Ms. Brennan to approve the payment as presented.
Second by Mr. U’Selis.
Questions on the motion – none.
Poll of the Board.
Motion carried unanimously.

· Consideration of Contract
· Second Street Pike Sewer Lining Project
· Performance Pipeling, Inc, CoStars contract # 535289

Motion by Mr. Monaghan to approve the contract as presented.
Second by Mr. Angermeier.
Questions on the motion – none.
Poll of the Board.
Motion carried unanimously.

· Consideration of Purchase
· New Holland Ford 2026 Ford Ranger 4x4

Motion by Mr. Monaghan to approve the purchase as presented.
Second by Ms. Brennan.
Questions on the motion – none.
Poll of the Board.
Motion carried unanimously.

9. Old Business
None

10. Adjourn to Executive Session
The meeting was adjourned to an executive session at 7:30 p.m.to discuss personnel.

11. Reconvene
The meeting was reconvened at 7:37 p.m. with no formal action having taken place.

12. Adjourn 
There be no further business before the Board, the chair entertained a motion for adjournment.

Motion by Mr. Monaghan 
Second by Mr. Angermeier.
Poll of the Board.
Motion carried unanimously.
The meeting adjourned at 7:38 p.m.



